HYDROCARBON POLLUTION REMEDIATION PROJECT (HYPREP)

Project Coordination Office -Environmental Remediation Unit

Environmental Remediation of Hydrocarbon Impacted Sites in Ogoniland, Rivers State.

Phase 2 Soil and Groundwater Remediation Works on Medium Risk Sites (SMR Lots)

WEEKLY SITE ASSESSMENT ACTIVITY REPORT

Reporting Week: 9					Date:04/09/2023 to 08/09/2023

Duration of Contract (in Months): 24		Flag-Off Date: 27/04/2023        Mobilization Date: 11/07/2023

Expected End Date: 11/07/2025                           Revised End Date: ….…/…..…/202…..

Duration on Site to Date (in Months -based on 22 Work Days per Month): 2Months/42 Days

1.0 SITE INFORMATION

| LOT NUMBER |  | SMR LOT 36 | CONTRACTOR: |  |  |  |  |  | PHILCOM INTEGRATED LIMITED |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| SITE NAME (Name/Community) |  |  |  |  | F/S FLARE SITE AREA 2 – KWAWA COMMUNITY |  |  |  |  |  |  | UNEP Code: |  |  | qc_016 - 001 |
| L. G. A | KHANA |  |  |  |  | SITE REFERENCE GPS COORDINATES (UTM, WGS84, ZONE 32N) |  |  |  |  |  | E:331632 |  |  | N: 509504 |
| Area (m2) of impacted soil: in the Bill of Quantities (BoQ) |  |  |  | 18,800M2 |  |  | Max depth of Impact (m) in the Bill of Quantities (BoQ) |  |  | 6.0m | Volume (m3) of Soil in the Bill of Quantities (BoQ) |  |  | 112,800m3 |  |
| Maximum initial Groundwater TPH (µg/l) in the Bill of Quantities (BoQ) |  |  |  |  |  |  |  | 77,000ug/l |  | Maximum initial Soil TPH (mg/kg) in the Bill of Quantities (BoQ) |  |  | 8,800mg/kg |  |  |

2.0 SITE INFRASTRUCTURE

| S/No | Site Infrastructures | Quantity | Size {(LxBxH) = ….m2/m3} -as applicable | Percentage Completion (%) | GPS Coordinates (UTM, WGS84, Zone 32N) |  | Remarks / Working Condition |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  | Easting | Northing |  |
| 1 | Site Offices | 1 | 27mx25mx3m | 100% | 331728 | 509657 | Completed |
| 2 | Sewage pit | 1 | 2.4mx1.2mx2.5m | 100% | 331761 | 509670 | Completed |
| 3 | Decontamination area | 1 | N/A |  |  |  | Not Yet |
| 4 | Engineered Biocell | 1 | 50mx50mx1.5m | 20% | 331743 | 509422 | Building Ongoing |
| 5 | Leachate sump | 1 | N/A |  |  |  | Not Yet |
| 6 | Security Post | 1 | 3mx2mx2.7m | 100% | 331728 | 509657 | Completed |
| 7 | Borehole/Stand | 1 | 0.6mx0.6mx15m | 100% | 331728 | 509657 | Completed |
| 8 | Workers Sit Out | 1 | 4.9mx4.9mx3.5m | 100% | 331755 | 509652 | Completed |
| 9 | Security Lights | 5 | 0.1mx0.1mx5m | 100% |  |  | Installed at the site office |
| 10 | Liquid Waste Point | 1 | 3.7mx1.2mx0.3m | 100% | 331763 | 509643 | Completed |

3.0 SITE HSE REPORT

3.1: Computation of Work Manhours

| A | B | C | D | E |
| --- | --- | --- | --- | --- |
| Total number of personnel on site | Number of days worked in the week | Number of days worked from inception to date | Week Manhours (A x B x 8hrs) | Project to Date Manhours (A x C x 8hrs) |
| 47 | 5 | 37 | 1,880 | 13,912 |

3.2: HSE Checks

| S/N | Work Description | Number | Cumulative | Remarks |
| --- | --- | --- | --- | --- |
| 1 | Toolbox Meetings / Talks | 5 | 37 | Toolbox carried out daily |
| 2 | Unsafe Acts / Unsafe Conditions / (UA/UC/) recorded | 3/0 | 11/2 | * Quarrel among workers * Horse Play * Lifting heavy object wrongly |
| 3 | Unsafe Acts / Unsafe Conditions (UA/UC/) Closed out | 3/0 | 11/2 | All UA/UC finally closeout |
| 4 | Near miss | 0 | 4 |  |
| 5 | First Aid case | 1 | 2 | Bruise was handled by site Nurse |
|  | Medical Treatment Case | 0 | 1 | The worker was taken to retainership clinic in Bori where he had some rest. |
| 6 | Environmental Incident | Nil | Nil |  |
| 7 | Work disruption by on-site community staff | Nil | Nil |  |
| 8 | Work disruption by off-site community intruders | Nil | Nil |  |
| 9 | Work disruption due to breakdown of work equipment such as excavator, tiller, or bulldozer. | 1 | 9 | Equipment broke down rectified |
| 10 | Lost hours due to equipment breakdown (Hrs) | 16 | 77 | Equipment finally in good condition |
| 11 | Waste management practices on site – housekeeping issues | Nil | Nil |  |
| 12 | Property/equipment damage | Nil | Nil |  |
| 13 | Fire incident | Nil | Nil |  |
| 14 | Monthly HSE meeting (s) | Nil | Nil |  |
| 15 | HSE training | Nil | Nil |  |
| 16 | No. of drills (Quarterly) | Nil | Nil |  |
| 17 | Fatality | Nil | Nil |  |

4.0 ASSESSMENT SAMPLING DATA

4.1: General Boreholes Information

| ITEM | QUANTITY | ITEM | QUANTITY |
| --- | --- | --- | --- |
| No. of Borehole Installed | 10 | Total No. of Soil Samples Collected | 90 (80 Organic (30 Speciated and 50 Non-Speciated), 10 Inorganic |
| No. of Auger holes Drilled | 10 | Total No. of Groundwater samples collected | 20 |

4.2: Boreholes Sampling Information

| S/N | Borehole Point ID | GPS Coordinates |  | Maximum Depth (mbgs) | Soil Sampling Intervals (mbgs) | Predominant Soil Lithology | No of soil samples collected per hole | Depth range of observed Impact (mbgs) | Predominant physical observation |  | Depth to Ground-water (mbgs) | Observed Impact on Ground-water (Y/N) |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | Easting | Northing |  |  |  |  |  | Odour | Sheen |  |  |
| 1 |  |  |  |  |  |  |  |  |  |  |  |  |
| 2 |  |  |  |  |  |  |  |  |  |  |  |  |
| 3 |  |  |  |  |  |  |  |  |  |  |  |  |
| 4 |  |  |  |  |  |  |  |  |  |  |  |  |
| 5 |  |  |  |  |  |  |  |  |  |  |  |  |
| 6 |  |  |  |  |  |  |  |  |  |  |  |  |
| 7 |  |  |  |  |  |  |  |  |  |  |  |  |
| 8 |  |  |  |  |  |  |  |  |  |  |  |  |
| 9 |  |  |  |  |  |  |  |  |  |  |  |  |
| 10 |  |  |  |  |  |  |  |  |  |  |  |  |
| 11 |  |  |  |  |  |  |  |  |  |  |  |  |

4.3: Auger holes Sampling Information

| S/N | Auger hole Point ID | GPS Coordinates |  | Maximum Depth (mbgs) | Soil Sampling Intervals (mbgs) | Predominant Soil Lithology | No of soil samples collected per hole | Depth range of observed Impact (mbgs) | Predominant physical observation |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | Easting | Northing |  |  |  |  |  | Odour | Sheen |
| 1 |  |  |  |  |  |  |  |  |  |  |
| 2 |  |  |  |  |  |  |  |  |  |  |
| 3 |  |  |  |  |  |  |  |  |  |  |
| 4 |  |  |  |  |  |  |  |  |  |  |
| 5 |  |  |  |  |  |  |  |  |  |  |
| 6 |  |  |  |  |  |  |  |  |  |  |
| 7 |  |  |  |  |  |  |  |  |  |  |
| 8 |  |  |  |  |  |  |  |  |  |  |
| 9 |  |  |  |  |  |  |  |  |  |  |
| 10 |  |  |  |  |  |  |  |  |  |  |
| 11 |  |  |  |  |  |  |  |  |  |  |
| 12 |  |  |  |  |  |  |  |  |  |  |
| 13 |  |  |  |  |  |  |  |  |  |  |
| 14 |  |  |  |  |  |  |  |  |  |  |
| 15 |  |  |  |  |  |  |  |  |  |  |
| 16 |  |  |  |  |  |  |  |  |  |  |

CHRONOLOGY OF ACTIVITIES

| S/NO | DATE | ACTIVITIES OF THE DAY | REMARK |
| --- | --- | --- | --- |
| 1 | MONDAY 04th September, 2023 | - Toolbox Meeting - Bio-Cell Preparation - General Housekeeping | find attached photos |
| 2 | TUESDAY 05th September, 2023 | - Toolbox Meeting - Sand Bagging by community workers - Slopping and Gradient of the Bio-Cell - General Housekeeping | find attached photos |
| 3 | WEDNESDAY 06th September, 2023 | - Toolbox meeting - Sewing of Sand Bags - Loading of Sand bags to Bio-Cell Area - General Housekeeping | find attached photos |
| 4 | THURSDAY 07th September, 2023 | - Toolbox meeting - Sewing of Sand Bags - Stagging of Sand bags in Bio-Cell Area - General Housekeeping | find attached photos |
| 5 | FRIDAY 08th September. 2023 | - Toolbox meeting - Sewing of Sand Bags - Loading of Sand bags to Bio-Cell Area - General Housekeeping | find attached photos |

Mr. Justice Barima

Project Manager

SITE PHOTOS

Plate 1: Toolbox Meeting

Plate 2: Sandbagging and Sewing Ongoing

Plate 3: Movement of Sandbags to Biocell Area by Community Workers

Plate 4: Weighing of Sand Bags Ongoing

Plate 5: Levelling of Biocell

Plate 6: Levelling of Biocell

Plate 7: Staging of Sand Bags

Plate 7: Staged Sand Bags in Bio-Cell Area

Plate 8: General House Keeping of the Office Area

Plate 9: House Keeping/Solid Waste Mgt.